## Sheet1
New topic/ question: performed by taskforce shepherded by Scientific Advisory Committee Representative
Deliverables (see accompanying document for further guidance) |  |  | Time (weeks) Estimate
1 | Develop/Confirm Search Strategy | Two chosen Taskforce Content experts develop broad question (Population, Intervention, Comparator, Outcomes) in consultation with the ILCOR taskforce and SAC working group member and approves/finalises the search strategy (may need IS help with this). The search strategy should include Medline, Embase and Cochrane with a (defensible) decision made about years to be searched (usually unrestricted); ERIC and CINHAL may be searched if applicable. | 2
2 | Title/abstract screening completed in duplicate and full text screening completed in duplicate | a. Clear guidance for inclusion and exclusion criteria agreed by taskforce (including study type). b. Title and abstract screening and full text screening both completed by two content experts. c. Outcomes are informed by review, and agreed by taskforce. | 2
3 | Review and discuss studies at Full Text Level to ensure all relevant studies included | Task force members asked to review included studies to see if any known to be missing. If a substantial number of articles are identified by these processes, a formal systematic review (via creation of PICOST, and usual SAC process)* or a Taskforce Systematic Review may be initiated. Risk of Bias assessments are not usually performed for scoping reviews. | 1*
4 | Data extraction | Data extraction including describing sub-groups as appropriate (Tables and Figures). Combination of data (meta-analyses) not required or necessary. | 2
5 | Preparation of summary document or manuscript as relevant | a. Prepare summary of scoping review for electronic appendix for CoSTR summary publication (note that Scoping reviews can not of themselves justify creation of new CoSTRs or amendment of existing CoSTRs). b. If sufficiently rigorous review, consider preparing manuscript for submission for Peer Review publication (compliant with PRISMA-SR checklist) c. Content experts update search just prior to submission for peer review. | 2
6 | Summary document posted for public comment | Summary document published on ILCOR.org for public comment | 1
7 | Summary document completed by TF for inclusion in CoSTR summary document | Taskforce submits final documents for ILCOR Board review | 1