## Sheet1
PICO revision from pre-existing question (2010/2015): performed by taskforce shepherded by Scientific Advisory Committee Representative
Deliverables (see accompanying document for further guidance) |  |  | Time (weeks)
1 | Develop/Confirm Search Strategy | Two chosen Taskforce Content experts finalize the Population, Intervention, Comparator, Outcomes, in consultation with the ILCOR taskforce and SAC working group member and approves/finalises the search strategy. The search strategy should include Medline, Embase and Cochrane with a (defensible) decision made about years to be searched; ERIC and CINHAL may be searched if applicable. Consideration for registration on Prospero if planning to publish separately as SR. | 2
2 | Title/abstract screening completed in duplicate and full text screening completed in duplicate | a. Clear guidance for inclusion and exclusion criteria agreed by taskforce. b. Outcomes agreed by taskforce. c. Title and abstract screening and full text screening completed in duplicate. d. Bias assessment performed by one content expert (confirmed by second) | 2
3 | Review and discuss studies at Full Text Level to ensure all relevant studies included | Task force mambers asked to review included studies to see if any known to be missing. If in the unusual circumstance that no important outcomes are found the review may not continue at this point. | 1
4 | Data extraction, verification and cleaning and preparation of draft meta-analyses (where appropriate) | Data extraction, verification and cleaning and preparation of draft meta- analyses (if appropriate) and a priori sub-group analysis (Tables and Figures) | 2
5 | Completion of Evidence Profile Tables | Updating/Completion of Evidence Profile Tables (eg. using GRADE PRO online resource (www.gradepro.org)) and creation of initial draft CoSTR | 1
6 | Task force review/approval of Evidence Profile Tables | Review of Evidence Profile Tables (eg. using GRADE PRO online resource (www.gradepro.org)) and the initial draft CoSTR, including consideration of steps from Evidence to Decision Framework | 2
7 | Preparation of draft COSTR & SR manuscript/appendix as relevant | a. Prepare the final draft CoSTR with accompanying GRADE Evidence Profile tables (considering steps from Evidence to Decision Framework) b. Prepare manuscript for submission for Peer Review (compliant with PRISMA checklist) or as electronic appendix for CoSTR publication c. The content experts will update the search just prior to submission for peer review. | 2
9 | CoSTR posted for public comment | CoSTR published on ILCOR.org for public comment | 1
10 | Final completion of CoSTR by TF for inclusion in summary document | Taskforce submits final documents including CoSTR for ILCOR Board review | 2